## Slide 1: Progress log
Internet of trash

## Slide 2: What did we want to achieve?
Make a project plan
Collect evidence
Start researching technologies

## Slide 3: How did we do it?
Divided up the work
Used creativity techniques
  SCAMPER
  Worst case scenario
  Progressive abstraction
Made pictures of evidence throughout the city
Technologies were researched online

## Slide 4: What were the results?
Creativity techniques lead to some new insights
Initial research lead to a shortlist of sensor technologies
Enough evidence to make a solid case was collected

## Slide 5: What were the problems?
Project planning didn’t suffice yet
We had to wait for contact with the local government
Creativity techniques were quite difficult to use sometimes

## Slide 6: What were the lessons learned?
Getting in touch with the stakeholders needs to be done as soon as possible
We learned how to use creativity techniques in our own context, and we found out their uses.

## Slide 7: What do we want to achieve?
Get in touch with the local government and van Gansewinkel
Implement feedback on the project plan
Set up a budget request for the sensor technologies
More goals will be defined this morning

## Slide 8: How are we going to do it?
Find out which people to contact
  Contact them
Find out material costs
  Are these costs within budget?
Feedback was received last week from monsieur
  Implement this feedback